## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | Ninth
Running or Final | Final
Cash Book Voucher No. and Date
Name of Contractor or supplier : | M/s. Shri Bajrang Construction, Padli Gujareshwar, Dungarpur
Name of Work ;- | Construction of Aamli Fala Bridge and Kherveda Nai Basti to Veeri Border Via Kuniya Vali Mata Road
Serial No. of this bill : | Ninth & Final Bill
No. and date of the last bill- | Not Applicable
Reference to work order or Agreement : | 1909 Dt. 17-07-2023
Agreement No. | 51/2023-24
WORK ORDER AMOUNT RS. | 39224443
Date of written order to commence work : | 2023-07-17
St. date of Start : | 2023-07-28
St. date of completion : | 2024-01-28
Date of actual completion of work :
Date of measurement :
TENDER PREMIUM % | 9.05
Premium Type | Below
Amount Paid Vide Last Bill

## Work Order
Item | Description | Unit | Quantity | Rate | Amount | BSR
1 | PART -" A" - EARTH WORK Clearing and grubbing road land including uprooting rank vegetation, grass, brush, shrubs, saplings and trees of girth upto 300mm, removal of stumps, disposal of unserviceable Material and stacking of serviceable Material upto 1000m from road boundary. (MoRTH Specification : Clause 201). BY MECHANICAL MEANS In area of Light Jungle | Hect. | 0.96 | 17206 | 16517.76
2 | Earthwork in excavation for roadway in soil, including stacking / disposal of surplus Material exclusive of compensation of earth (MoRTH specification : clause 301 to 305). By Hydraulic Excavator CK-90 of 0.9 cum bucket capacity and tipper with disposal upto 1000 mtrs. | cum | 32746 | 26 | 851396
3 | Earthwork in excavation in ordinary rock, including stacking / disposal of surplus Material exclusive of compensation of earth (MoRTH specification : clause 301 to 305). By Hydraulic Excavator CK-90 of 0.9 cum bucket capacity and tipper with disposal upto 1000 mtrs. | cum | 10291.6 | 34 | 349914.4
4 | Earthwork in excavation for roadway in hard rock, including stacking / disposal of surplus Material exclusive of compensation of earth (MoRTH specification : clause 301 to 305). Blasting prohibited By Mechanical Means | cum | 3742.4 | 309 | 1156401.6
5 | Construction of embankment with approved Material obtained from borrow-pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacting by vibratory roller 8-10 tonne to meet requirement of Table 300-2 including cost of compensation for earth taken from private land with lead upto 1 km as per MoRTH Specification : Clause No. 305. | cum | 13840 | 52 | 719680
6 | Construction of embankment with approved Materials deposited at site from roadway cutting and excavation from drain and foundation of other structures graded and compacted by vibratory roller 8-10 tonne to meet requirement of Tale 300-2 as per MoRTH specification : Clause No. 305 | cum | 46780 | 19 | 888820
7 | Construction of sub-grade and earthen shoulders with approved Material obtained from borrow-pits with all lifts and leads, transporting to site, spreading, grading to require slope and compacted by vibratory roller 8-10 tonne to meet requirement of Table 300-2 as per MoRTH specification : Clause No. 305. | cum | 3966.02 | 54 | 214165.08
8 | PART -" B" - WBM & Hard Shoulder Providing, laying and spreading of granular sub-base by providing coarse graded Material, spreading in uniform layers with motor grader on prepared surface mixing by mix in place method with rotavator at OMC, and compacting with vibratory roller to achieve the desired density, complete as per MoRTH Specification : clause No. 401. Grading-II | Cum | 2478.6 | 848 | 2101852.8
9 | Providing, laying, spreading and compacting crushed graded stone aggregate as per Table 400-10 & 400.11 to Wet Mix Macadam specifications including premixing the Material with water to OMC in mechanical mixer (Pug mill) as per design mix, carriage of mixed Material by tipper to site laying in uniform layers, with motor grader/F.E. loader/Paver Finisher, in sub- base/base course on a well prepared under base and compacting with Vibratory Roller to achieve the desired density including lighting, guarding, barricading and maintenance of Driversion etc. (MoRTH specification : Clause 406). with all lead & lift By mechanical means | Cum | 2295 | 1056 | 2423520
10 | PART -" C" - B.T. Work Providing and applying primer coat over prepared surface of granular base with bitumen emulsion as per IS:8887 & manufacturer’s specifications @6 kg/10 sqm with a self propelled or towed bitumen pressure sprayer equipped for spraying the Material uniformly at specified rates and temperatures (including cleaning of road surface) as per MoRTH specification : Cl. 502, 112 | Sqm. | 15300 | 25.26 | 386478
11 | Providing and laying open graded premix carpet 20mm thick (compacted), on prepared surface in a single course as wearing course, composed of specified graded crushed aggregates as per Table 500-23, heating bituminous binder @ 14.6 kg/10 sqm and aggregates in Hot Mix Plant (including cost of anti-stripping compound, wherever required), transporting the mixed Material with tipper and laying with paver finisher to the required level and grade, rolling with power roller, 8-10 tonne, but excluding cost of tack coat and seal coat with lead for mix of Material 1 km (MoRTH specification : clause 510, 112) In Hot Mix Plant 40-60 TPH, including loading of aggregates with F.E. loader bitumen VG30 grade | Sqm. | 15300 | 94 | 1438200
12 | Providing and applying Premixed Seal Coat type “B” comprising of thin application of fine aggregate (0.06 cum per 10 sqm) premix with (6.8 kg per 10 sqm) bitumen binder (including cost of anti-stripping compound, wherever required) in mini hot mix plant 6-10 TPH, and laying with paver finisher and rolling with power roller 8-10 tonne, including all lead of mix Material (MoRTH specification : clause 511). Bitumen VG30 grade | Sqm. | 15300 | 31 | 474300
13 | Part- D :- Road Furnishing Kilometre Stone Reinforced cement concrete M15grade kilometre stone of standard design as per IRC:8-1980, fixing in position including painting and printing etc Ordinary kilometer stone (precast) | No | 5 | 1501 | 7505
14 | Hectometer stone (precast) | No | 20 | 410 | 8200
15 | Boundary pillar Reinforced cement concrete M15 grade boundary pillars of standard design as per IRC:25-1967, fixed in position including finishing and lettering but excluding painting | No | 48 | 375 | 18000
16 | Providing and Fixing of Retro Reflectorised 900mm Cautionary sign boards made out of retro reflective sheeting of micro prismatic grade conforming to IRC-67: 2012 & Type XI standards of ASTM D4956-09 specifications, fixed over 2 mm thick Al / 4mm thick ACP sheet supported with Back support frame of 25x25x3mm mild steel angle as approved , supported on a mild steel angle iron post 75 mm X 75 mm X 6 mm - 3 mtr height, firmly fixed to the ground by means of properly designed foundation with M20 grade cement concrete 45 cm X 45 cm X 60 cm , 60 cm below ground level as per approved drawing. 10 years Warranty for Retro Reflective Sheeting from the original sheeting manufacturer & a certified copy of three years outdoor exposure report from an independent test lab for the product offered shall be submitted by the contractor. (This shall be used only for N.H, S.H & M.S.H Roads). Regulatory sign boards of 90 cm Triangle. Size 90 cms. Triangle | No | 8 | 3792 | 30336
17 | Providing and Fixing of Retro Reflectorised 600 x 800 mm Facility sign boards made out of retro reflective sheeting of micro prismatic grade conforming to IRC-67: 2012 & TypeXI standards of ASTM D4956-09 specifications, fixed over 2 mm thick Al / 4mm thick ACP sheet supported with Back support frame of 25x25x3mm mild steel angle as approved , supported on a mild steel angle iron post 75 mm X 75 mm X 6 mm - 3 mtr height, firmly fixed to the ground by means of properly designed foundation with M20 grade cement concrete 45 cm X 45 cm X 60 cm , 60 cm below ground level as per approved drawing. 10 years Warranty for Retro Reflective Sheeting from the original sheeting manufacturer & a certified copy of three years outdoor exposure report from an independent test lab for the product offered shall be submitted by the contractor. (This shall be used only for N.H, S.H & M.S.H Roads). Regulatory sign boards of 60 x 80 cm Rectangle. Size 60 x 80 cms. Rectangle | No | 8 | 4674 | 37392
18 | Providing and Fixing of Retro Reflectorised direction & place identification sign boards made out of retro reflective sheeting of High Intensity prismatic grade conforming to IRC-67: 2012 & Type XI standards of ASTM D4956-09 specifications, fixed over 2mm thick Al / 4 mm thick ACP sheet supported with Back support frame of 35x35x5mm mild steel angle with areas not exceeding 0.9 sqm. Supported in mild steel angle iron post 75x75x6mm - 3 mtr height ,firmly fixed to the grounf by means of properly designed foundation of M20 grade cement concrete 45 cm X 45 cm X 60 cm , 60 cm below ground level complete (as per MoRT&H specification No.801) (for area Less than 0.9 sqm). 10 years Warranty for Retro Reflective Sheeting from the original sheeting manufacturer & a certified copy of three years outdoor exposure report from an independent test lab for the product offered shall be submitted by the contractor. (This shall be used only for N.H, S.H & M.S.H Roads). Direction Sign boards below 0.9 Sq.Mtr Size Less than 0.9 SQ.Mtr Direction Sign Board | No | 8 | 7132 | 57056
19 | Road Marking with Hot Applied Thermoplastic Compound with Reflectorising Glass Beads on Bituminous Surface Providing and laying of hot applied thermoplastic compound 2.5 mm thick including reflectorising glass beads @ 250 gms per sqm area, thickness of 2.5 mm is exclusive of surface applied glass beads as per IRC:35 .The finished surface to be level, uniform and free from streaks and holes. | Sqm | 1240 | 408 | 505920
20 | Flexible Crash Barrier, Wire Rope Safety Barrier Providing and erecting a wire rope safety barrier with vertical posts of medium weight RS Joist (ISMB series) 100 mm x 75 mm (11.50 kg/m), 1.50 m long 0.85 m above ground and 0.65 m below ground level, split at the bottom for better grip, embedded in M 15 grade cement concrete 450 x 450 x 450 mm, 1.50 m center to center and with 4 horizontal steel wire rope 40 mm dia and anchored at terminal posts 15 m apart. Terminal post to be embedded in M 15 grade cement concrete foundation 2400 x 450 x 900 mm (depth), strengthened by a strut of RS joist 100 x 75 mm, 2 m long at 450 inclination and a tie 100 x 8 mm, 1.50 m long at the bottom, all embedded in foundation concrete as per approved design and drawing, rate excluding excavation and cement concrete. | Running metre | 15 | 1768 | 26520
21 | Part ''E'' CD Work Earthwork in excavation for foundation of structure complete with all lift, dewatering, shoring and shuttering etc. including refilling of trenches in 250 mm layer, ramming, watering and disposal of surplus soil within a lead of 1000 meters, as per drawing and technical Earth in excavation for foundation of specification. [MoRTH Specification : Clause 304]. n ordinary soil [MoRTH Specification : clause 301] BY MECHANICAL MEANS Depth upto 3m
21.01 | 1000mm dia HP 1 Row | cum | 681.84 | 57 | 38864.88
21.02 | 1000mm dia HP 2 Row | cum | 450.8 | 57 | 25695.6
21.03 | RCC Bridge | cum | 617.016 | 57 | 35169.91
21.04 | Syphon | cum | 95.84 | 57 | 5462.88
21.05 | Retaining wall | cum | 1680 | 57 | 95760
21.06 | VCW | cum | 1252.5 | 57 | 71392.5
22 | Earthwork in excavation for foundation of structure complete with all lift, dewatering, shoring and shuttering etc. including refilling of trenches in 250 mm layer, ramming, watering and disposal of surplus soil within a lead of 1000 meters, as per drawing and technical Earth in excavation for foundation of specification. [MoRTH Specification : Clause 304].In Ordinary/Soft rock (not requiring blasting) [MoRTH Specification : Clause 301] BY MECHANICAL MEANS
22.01 | RCC Bridge | cum | 666.27 | 83 | 55300.41
23 | Earthwork in excavation for foundation of structure complete with all lift, dewatering, shoring and shuttering etc. including refilling of trenches in 250 mm layer, ramming, watering and disposal of surplus soil within a lead of 1000 meters, as per drawing and technical Earth in excavation for foundation of specification. [MoRTH Specification : Clause 304]. In Hard Rock [MoRTH Specification : Clause 301, 302, 303]. Blasting Prohibited
23.01 | RCC Bridge | cum | 456.27 | 670 | 305700.9
24 | Plain Cement Concrete 1:3:6 with 40mm nominal mix in foundation with crushed stone aggregate 40mm nominal size mechanically mixed, placed in foundation and compacted by vibrator including curing for 14 days. (MoRTH specification clause : 2100)
24.01 | 1000mm dia HP 1 Row | cum | 46.44 | 3038 | 141084.72
24.02 | 1000mm dia HP 2 Row | cum | 26.8 | 3038 | 81418.4
24.03 | Retaining wall | cum | 167.99 | 3038 | 510353.62
24.04 | VCW | cum | 80.7 | 3038 | 245166.6
25 | Structural cement concrete (Design Mix) in open foundations, with form work, at any level. Cement concrete for plain/reinforced concrete in open foundations as per drawing and technical specification. [MoRTH Specification : Section 1700 & 1500]. With 20mm nominal size aggregate P.C.C. M-20 grade
25.01 | RCC Bridge | cum | 74.43 | 4017 | 298985.31
26 | Structural cement concrete (Design Mix) in open foundations, with form work, at any level. Cement concrete for plain/reinforced concrete in open foundations as per drawing and technical specification. [MoRTH Specification : Section 1700 & 1500]. With 20mm nominal size aggregate R.C.C. M-25 grade
26.01 | RCC Bridge | cum | 465.18 | 4341 | 2019346.38
27 | Providing and laying Plain Cement Concrete M-15 mix with stone aggregate 20mm nominal size mechanically mixed and vibrated in foundation upto a depth of 1.50 below ground level and or 1.50mtr. above ground/bed level.
27.01 | 1000mm dia HP 1 Row | cum | 409.5 | 3666 | 1501227
27.02 | 1000mm dia HP 2 Row | cum | 225.36 | 3666 | 826169.76
27.03 | Syphon | cum | 41.481 | 3666 | 152069.35
27.04 | Retaining wall | cum | 1531.25 | 3666 | 5613562.5
27.05 | VCW | cum | 629.53 | 3666 | 2307856.98
28 | Providing and laying Plain Cement Concrete M-15 Mix with stone aggregate 20mm nominal size mechanically mixed and vibrated, in superstructure upto 4 meter above 1.50 m level from ground/bed level. [MoRTH Specification : Clause 1000/1700]
28.01 | 1000mm dia HP 1 Row | cum | 3.42 | 3850 | 13167
28.02 | 1000mm dia HP 2 Row | cum | 1.52 | 3850 | 5852
28.03 | VCW | cum | 6.934 | 3850 | 26695.9
29 | Providing and laying Reinforced cement concrete pipes NP-3 for culverts including jointing ends and fixing collar with cement mortar 1:2. (MoRTH specification : clause 1000/2900). 1000mm dia
29.01 | 1000mm dia HP 1 Row | RM | 135 | 4410 | 595350
29.02 | 1000mm dia HP 2 Row | RM | 120 | 4410 | 529200
29.03 | VCW | RM | 75 | 4410 | 330750
30 | Providing and laying Reinforced cement concrete pipes NP-3 for culverts including jointing ends and fixing collar with cement mortar 1:2. (MoRTH specification : clause 1000/2900) 500mm dia
30.01 | Syphon | RM | 60 | 2243 | 134580
31 | Providing and laying RCC M-20 mix with stone aggregate 20mm (nominal size) mechanically mixed and vibrated for RCC work in slab in superstructure upto 4 mtr. above 1.5 mtr. level from Bed/Ground level, excluding steel reinforcement but including centering and shuttering, laid in position. (MoRTH specification : Clause 1000/1700)
31.01 | Syphon | cum | 2.1 | 4528 | 9508.8
31.02 | VCW | cum | 73.388 | 4528 | 332300.86
32 | Plastering 20mm thick with cement mortar (1:3) on Masonry work in sub structure as per technical specifications.
32.01 | Syphon | sqm. | 83.52 | 139 | 11609.28
32.02 | VCW | sqm. | 161.69 | 139 | 22474.91
33 | Structural cement concrete (Design Mix) in open foundations, with form work, at any level. Cement concrete for plain/reinforced concrete in open foundations as per drawing and technical specification. [MoRTH Specification : Section 1700 & 1500]. With 20mm nominal size aggregate P.C.C. M-15 grade
33.01 | RCC Bridge | cum | 162.793 | 3590 | 584426.87
34 | Structural cement concrete for plain concrete/ reinforced concrete for substructure at any level, complete as per drawing and technical specification. Design mix concrete – [MoRTH Specification : Section 1500 & 1700]. PCC M-25 grade Upto 5 mtr. Height
34.01 | RCC Bridge | cum | 352.953 | 3915 | 1381811
35 | Providing A.C. pipe Weep holes 150mm dia in Masonry/plain Concrete/Reinforced Concrete abutment, wing wall/return wall complete as per drawing and technical specification. [MoRTH Specification : Clause 2205].
35.01 | Retaining wall | R.Mtr. | 120 | 114 | 13680
35.02 | RCC Bridge | R.Mtr. | 420 | 114 | 47880
36 | Steel reinforcement in substructure complete. [MoRTH Specification : Section 1600] HYSD reinforcement
36.01 | RCC Bridge | Tonne | 52.508 | 88737 | 4659402.4
36.02 | VCW | Tonne | 4.403 | 88737 | 390709.01
37 | Providing and laying steel reinforcement at any level in foundation complete as per drawing and technical specification. [MoRTH Specification : Section 1600]. HYSD bar reinforcement
37.01 | RCC Bridge | Tonne | 43.82 | 88567 | 3881005.94
38 | Structural RCC/PSC upto a height of 5 mtr. for reinforced concrete in superstructure complete including steel formwork, scaffolding etc. As per drawing and technical specification.Design mix concrete. [MoRTH Specification : 1500 & 1700].RCC M-30 grade Solid slab superstructure
38.01 | RCC Bridge | cum | 211.578 | 6307 | 1334422.45
39 | Reinforced cement concrete wearing coat M-30 grade at any level including formwork and reinforcement complete as per drawing and technical Specification. [MoRTH Specification : Clause 2204, 1500 & 1700].
39.01 | RCC Bridge | cum | 25.5 | 7720 | 196860
40 | Providing and Laying PCC M-15 grade leveling course below approach slab complete as per drawing and technical specifications. [MoRTH specification : 2700]
40.01 | RCC Bridge | cum | 10.53 | 2471 | 26019.63
41 | Reinforced cement concrete M-30 grade approach slab including reinforcement and formwork complete as per drawing and technical specifications. [MoRTH specification : 1500, 1600, 1700, 2704]
41.01 | RCC Bridge | cum | 21.06 | 7073 | 148957.38
42 | Providing and laying HYSD bar reinforcement at any level in superstructure complete as per drawing and technical Specification. [MoRTH Specification : Section 1600]
42.01 | RCC Bridge | Tonne | 19.931 | 89654 | 1786893.87
43 | Providing and filling in foundation trenches, and back filling behind abutments, wing walls, return wall etc., and below pipe bed in layers not exceeding 150mm thick including watering and compacting (IRC-78) complete as per drawing and technical specifications (MoRTH specification 710 & 2200) including all lead and lifts. Selected granular Material in filling (MoRTH specification : Clause 2200).
43.01 | RCC Bridge | cum | 246.32 | 745 | 183508.4
44 | Filter medium behind abutment, wing wall and return wall, complete as per drawing and technical specification. (Same as R7.20.3) [MoRTH Specification : Clause 2504].
44.01 | RCC Bridge | cum | 83.16 | 560 | 46569.6
45 | Providing, laying and fixing of Filler Joint Providing and fixing 2mm thick Corrugated Copper Plate in expansion joint complete as per drawing and technical specifications in MoRTH specification : clause 2605.
45.01 | RCC Bridge | Mtr | 25.5 | 3673 | 93661.5
46 | Supply of flood gauge (water gauge) as per IRC 67 standard 200cm long fixed on angle iron posts 50×50×6mm 2.6m long
46.01 | RCC Bridge | Nos | 2 | 1383 | 2766
47 | Providing and Laying un-reinforced, dowel jointed, plain cement concrete pavement over a prepared sub-base with 43 grade cement, coarse and fine aggregate conforming to IS:383, maximum size of coarse aggregate not exceeding 25mm, mixed in a batching and mixing plant as per approved mix design, transported to site, laid with a fixed form or slip form paver, spread, compacted and finished in a continuous operation including provision of contraction, expansion, construction and longitudinal joints, joint filler, separation membrane, sealant primer, joint sealant, debonding strip, dowel bar, tie rod, admixtures and vacuum processing pump as approved, curing compound, finishing to lines and grades as per drawing as per MoRTH Specification : Clause No. 602, 112.Using Cement concrete M-20 pavement Grade
47.01 | RCC Bridge | cum | 34.425 | 4747 | 163415.48
48 | Providing and laying graded stone aggregate filter Material underneath pitching on slopes complete as per drawing and technical specification. (MoRTH specification : clause 2504).
48.01 | VCW | Cum | 139.32 | 942 | 131239.44
| Total |  |  |  | 43127480.06
| Add Tender Premium | % | 9.05 | Below | -3903037
| Grand Total |  |  |  | 39224443.06
Prit

## Bill Quantity
Item | Description | Unit | Quantity | Rate | Amount | BSR
1 | PART -" A" - EARTH WORK Clearing and grubbing road land including uprooting rank vegetation, grass, brush, shrubs, saplings and trees of girth upto 300mm, removal of stumps, disposal of unserviceable Material and stacking of serviceable Material upto 1000m from road boundary. (MoRTH Specification : Clause 201). BY MECHANICAL MEANS In area of Light Jungle | Hect. | 0.96 | 17206 | 16517.76
2 | Earthwork in excavation for roadway in soil, including stacking / disposal of surplus Material exclusive of compensation of earth (MoRTH specification : clause 301 to 305). By Hydraulic Excavator CK-90 of 0.9 cum bucket capacity and tipper with disposal upto 1000 mtrs. | cum | 47317.97 | 26 | 1230267.22
3 | Earthwork in excavation in ordinary rock, including stacking / disposal of surplus Material exclusive of compensation of earth (MoRTH specification : clause 301 to 305). By Hydraulic Excavator CK-90 of 0.9 cum bucket capacity and tipper with disposal upto 1000 mtrs. | cum | 15072.05 | 34 | 512449.7
4 | Earthwork in excavation for roadway in hard rock, including stacking / disposal of surplus Material exclusive of compensation of earth (MoRTH specification : clause 301 to 305). Blasting prohibited By Mechanical Means | cum | 5579.92 | 309 | 1724195.28
5 | Construction of embankment with approved Material obtained from borrow-pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacting by vibratory roller 8-10 tonne to meet requirement of Table 300-2 including cost of compensation for earth taken from private land with lead upto 1 km as per MoRTH Specification : Clause No. 305. | cum | 19798.12 | 52 | 1029502.24
6 | Construction of embankment with approved Materials deposited at site from roadway cutting and excavation from drain and foundation of other structures graded and compacted by vibratory roller 8-10 tonne to meet requirement of Tale 300-2 as per MoRTH specification : Clause No. 305 | cum | 68906.94 | 19 | 1309231.86
7 | Construction of sub-grade and earthen shoulders with approved Material obtained from borrow-pits with all lifts and leads, transporting to site, spreading, grading to require slope and compacted by vibratory roller 8-10 tonne to meet requirement of Table 300-2 as per MoRTH specification : Clause No. 305. | cum | 3966.02 | 54 | 214165.08
8 | PART -" B" - WBM & Hard Shoulder Providing, laying and spreading of granular sub-base by providing coarse graded Material, spreading in uniform layers with motor grader on prepared surface mixing by mix in place method with rotavator at OMC, and compacting with vibratory roller to achieve the desired density, complete as per MoRTH Specification : clause No. 401. Grading-II | Cum | 2478.6 | 848 | 2101852.8
9 | Providing, laying, spreading and compacting crushed graded stone aggregate as per Table 400-10 & 400.11 to Wet Mix Macadam specifications including premixing the Material with water to OMC in mechanical mixer (Pug mill) as per design mix, carriage of mixed Material by tipper to site laying in uniform layers, with motor grader/F.E. loader/Paver Finisher, in sub- base/base course on a well prepared under base and compacting with Vibratory Roller to achieve the desired density including lighting, guarding, barricading and maintenance of Driversion etc. (MoRTH specification : Clause 406). with all lead & lift By mechanical means | Cum | 2295 | 1056 | 2423520
10 | PART -" C" - B.T. Work Providing and applying primer coat over prepared surface of granular base with bitumen emulsion as per IS:8887 & manufacturer’s specifications @6 kg/10 sqm with a self propelled or towed bitumen pressure sprayer equipped for spraying the Material uniformly at specified rates and temperatures (including cleaning of road surface) as per MoRTH specification : Cl. 502, 112 | Sqm. | 15300 | 25.26 | 386478
11 | Providing and laying open graded premix carpet 20mm thick (compacted), on prepared surface in a single course as wearing course, composed of specified graded crushed aggregates as per Table 500-23, heating bituminous binder @ 14.6 kg/10 sqm and aggregates in Hot Mix Plant (including cost of anti-stripping compound, wherever required), transporting the mixed Material with tipper and laying with paver finisher to the required level and grade, rolling with power roller, 8-10 tonne, but excluding cost of tack coat and seal coat with lead for mix of Material 1 km (MoRTH specification : clause 510, 112) In Hot Mix Plant 40-60 TPH, including loading of aggregates with F.E. loader bitumen VG30 grade | Sqm. | 15300 | 94 | 1438200
12 | Providing and applying Premixed Seal Coat type “B” comprising of thin application of fine aggregate (0.06 cum per 10 sqm) premix with (6.8 kg per 10 sqm) bitumen binder (including cost of anti-stripping compound, wherever required) in mini hot mix plant 6-10 TPH, and laying with paver finisher and rolling with power roller 8-10 tonne, including all lead of mix Material (MoRTH specification : clause 511). Bitumen VG30 grade | Sqm. | 15300 | 31 | 474300
13 | Part- D :- Road Furnishing Kilometre Stone Reinforced cement concrete M15grade kilometre stone of standard design as per IRC:8-1980, fixing in position including painting and printing etc Ordinary kilometer stone (precast) | No | 5 | 1501 | 7505
14 | Hectometer stone (precast) | No | 20 | 410 | 8200
15 | Boundary pillar Reinforced cement concrete M15 grade boundary pillars of standard design as per IRC:25-1967, fixed in position including finishing and lettering but excluding painting | No | 48 | 375 | 18000
16 | Providing and Fixing of Retro Reflectorised 900mm Cautionary sign boards made out of retro reflective sheeting of micro prismatic grade conforming to IRC-67: 2012 & Type XI standards of ASTM D4956-09 specifications, fixed over 2 mm thick Al / 4mm thick ACP sheet supported with Back support frame of 25x25x3mm mild steel angle as approved , supported on a mild steel angle iron post 75 mm X 75 mm X 6 mm - 3 mtr height, firmly fixed to the ground by means of properly designed foundation with M20 grade cement concrete 45 cm X 45 cm X 60 cm , 60 cm below ground level as per approved drawing. 10 years Warranty for Retro Reflective Sheeting from the original sheeting manufacturer & a certified copy of three years outdoor exposure report from an independent test lab for the product offered shall be submitted by the contractor. (This shall be used only for N.H, S.H & M.S.H Roads). Regulatory sign boards of 90 cm Triangle. Size 90 cms. Triangle | No | 8 | 3792 | 30336
17 | Providing and Fixing of Retro Reflectorised 600 x 800 mm Facility sign boards made out of retro reflective sheeting of micro prismatic grade conforming to IRC-67: 2012 & TypeXI standards of ASTM D4956-09 specifications, fixed over 2 mm thick Al / 4mm thick ACP sheet supported with Back support frame of 25x25x3mm mild steel angle as approved , supported on a mild steel angle iron post 75 mm X 75 mm X 6 mm - 3 mtr height, firmly fixed to the ground by means of properly designed foundation with M20 grade cement concrete 45 cm X 45 cm X 60 cm , 60 cm below ground level as per approved drawing. 10 years Warranty for Retro Reflective Sheeting from the original sheeting manufacturer & a certified copy of three years outdoor exposure report from an independent test lab for the product offered shall be submitted by the contractor. (This shall be used only for N.H, S.H & M.S.H Roads). Regulatory sign boards of 60 x 80 cm Rectangle. Size 60 x 80 cms. Rectangle | No | 8 | 4674 | 37392
18 | Providing and Fixing of Retro Reflectorised direction & place identification sign boards made out of retro reflective sheeting of High Intensity prismatic grade conforming to IRC-67: 2012 & Type XI standards of ASTM D4956-09 specifications, fixed over 2mm thick Al / 4 mm thick ACP sheet supported with Back support frame of 35x35x5mm mild steel angle with areas not exceeding 0.9 sqm. Supported in mild steel angle iron post 75x75x6mm - 3 mtr height ,firmly fixed to the grounf by means of properly designed foundation of M20 grade cement concrete 45 cm X 45 cm X 60 cm , 60 cm below ground level complete (as per MoRT&H specification No.801) (for area Less than 0.9 sqm). 10 years Warranty for Retro Reflective Sheeting from the original sheeting manufacturer & a certified copy of three years outdoor exposure report from an independent test lab for the product offered shall be submitted by the contractor. (This shall be used only for N.H, S.H & M.S.H Roads). Direction Sign boards below 0.9 Sq.Mtr Size Less than 0.9 SQ.Mtr Direction Sign Board | No | 8 | 7132 | 57056
19 | Road Marking with Hot Applied Thermoplastic Compound with Reflectorising Glass Beads on Bituminous Surface Providing and laying of hot applied thermoplastic compound 2.5 mm thick including reflectorising glass beads @ 250 gms per sqm area, thickness of 2.5 mm is exclusive of surface applied glass beads as per IRC:35 .The finished surface to be level, uniform and free from streaks and holes. | Sqm | 1240 | 408 | 505920
20 | Flexible Crash Barrier, Wire Rope Safety Barrier Providing and erecting a wire rope safety barrier with vertical posts of medium weight RS Joist (ISMB series) 100 mm x 75 mm (11.50 kg/m), 1.50 m long 0.85 m above ground and 0.65 m below ground level, split at the bottom for better grip, embedded in M 15 grade cement concrete 450 x 450 x 450 mm, 1.50 m center to center and with 4 horizontal steel wire rope 40 mm dia and anchored at terminal posts 15 m apart. Terminal post to be embedded in M 15 grade cement concrete foundation 2400 x 450 x 900 mm (depth), strengthened by a strut of RS joist 100 x 75 mm, 2 m long at 450 inclination and a tie 100 x 8 mm, 1.50 m long at the bottom, all embedded in foundation concrete as per approved design and drawing, rate excluding excavation and cement concrete. | Running metre | 15 | 1768 | 26520
21 | Part ''E'' CD Work Earthwork in excavation for foundation of structure complete with all lift, dewatering, shoring and shuttering etc. including refilling of trenches in 250 mm layer, ramming, watering and disposal of surplus soil within a lead of 1000 meters, as per drawing and technical Earth in excavation for foundation of specification. [MoRTH Specification : Clause 304]. n ordinary soil [MoRTH Specification : clause 301] BY MECHANICAL MEANS Depth upto 3m
21.01 | 1000mm dia HP 1 Row | cum | 681.84 | 57 | 38864.88
21.02 | 1000mm dia HP 2 Row | cum | 450.8 | 57 | 25695.6
21.03 | RCC Bridge | cum | 618.58 | 57 | 35259.06
21.04 | Syphon | cum | 95.84 | 57 | 5462.88
21.05 | Retaining wall | cum | 1680 | 57 | 95760
21.06 | VCW | cum | 1252.5 | 57 | 71392.5
22 | Earthwork in excavation for foundation of structure complete with all lift, dewatering, shoring and shuttering etc. including refilling of trenches in 250 mm layer, ramming, watering and disposal of surplus soil within a lead of 1000 meters, as per drawing and technical Earth in excavation for foundation of specification. [MoRTH Specification : Clause 304].In Ordinary/Soft rock (not requiring blasting) [MoRTH Specification : Clause 301] BY MECHANICAL MEANS
22.01 | RCC Bridge | cum | 990.08 | 83 | 82176.64
23 | Earthwork in excavation for foundation of structure complete with all lift, dewatering, shoring and shuttering etc. including refilling of trenches in 250 mm layer, ramming, watering and disposal of surplus soil within a lead of 1000 meters, as per drawing and technical Earth in excavation for foundation of specification. [MoRTH Specification : Clause 304]. In Hard Rock [MoRTH Specification : Clause 301, 302, 303]. Blasting Prohibited
23.01 | RCC Bridge | cum | 1088.31 | 670 | 729167.7
24 | Plain Cement Concrete 1:3:6 with 40mm nominal mix in foundation with crushed stone aggregate 40mm nominal size mechanically mixed, placed in foundation and compacted by vibrator including curing for 14 days. (MoRTH specification clause : 2100)
24.01 | 1000mm dia HP 1 Row | cum | 46.44 | 3038 | 141084.72
24.02 | 1000mm dia HP 2 Row | cum | 26.8 | 3038 | 81418.4
24.03 | Retaining wall | cum | 167.99 | 3038 | 510353.62
24.04 | VCW | cum | 80.7 | 3038 | 245166.6
25 | Structural cement concrete (Design Mix) in open foundations, with form work, at any level. Cement concrete for plain/reinforced concrete in open foundations as per drawing and technical specification. [MoRTH Specification : Section 1700 & 1500]. With 20mm nominal size aggregate P.C.C. M-20 grade
25.01 | RCC Bridge | cum | 114.44 | 4017 | 459705.48
26 | Structural cement concrete (Design Mix) in open foundations, with form work, at any level. Cement concrete for plain/reinforced concrete in open foundations as per drawing and technical specification. [MoRTH Specification : Section 1700 & 1500]. With 20mm nominal size aggregate R.C.C. M-25 grade
26.01 | RCC Bridge | cum | 961.61 | 4341 | 4174349.01
27 | Providing and laying Plain Cement Concrete M-15 mix with stone aggregate 20mm nominal size mechanically mixed and vibrated in foundation upto a depth of 1.50 below ground level and or 1.50mtr. above ground/bed level.
27.01 | 1000mm dia HP 1 Row | cum | 409.5 | 3666 | 1501227
27.02 | 1000mm dia HP 2 Row | cum | 225.36 | 3666 | 826169.76
27.03 | Syphon | cum | 41.481 | 3666 | 152069.346
27.04 | Retaining wall | cum | 1531.25 | 3666 | 5613562.5
27.05 | VCW | cum | 629.53 | 3666 | 2307856.98
28 | Providing and laying Plain Cement Concrete M-15 Mix with stone aggregate 20mm nominal size mechanically mixed and vibrated, in superstructure upto 4 meter above 1.50 m level from ground/bed level. [MoRTH Specification : Clause 1000/1700]
28.01 | 1000mm dia HP 1 Row | cum | 3.42 | 3850 | 13167
28.02 | 1000mm dia HP 2 Row | cum | 1.52 | 3850 | 5852
28.03 | VCW | cum | 6.934 | 3850 | 26695.9
29 | Providing and laying Reinforced cement concrete pipes NP-3 for culverts including jointing ends and fixing collar with cement mortar 1:2. (MoRTH specification : clause 1000/2900). 1000mm dia
29.01 | 1000mm dia HP 1 Row | RM | 135 | 4410 | 595350
29.02 | 1000mm dia HP 2 Row | RM | 120 | 4410 | 529200
29.03 | VCW | RM | 75 | 4410 | 330750
30 | Providing and laying Reinforced cement concrete pipes NP-3 for culverts including jointing ends and fixing collar with cement mortar 1:2. (MoRTH specification : clause 1000/2900) 500mm dia
30.01 | Syphon | RM | 60 | 2243 | 134580
31 | Providing and laying RCC M-20 mix with stone aggregate 20mm (nominal size) mechanically mixed and vibrated for RCC work in slab in superstructure upto 4 mtr. above 1.5 mtr. level from Bed/Ground level, excluding steel reinforcement but including centering and shuttering, laid in position. (MoRTH specification : Clause 1000/1700)
31.01 | Syphon | cum | 2.1 | 4528 | 9508.8
31.02 | VCW | cum | 73.388 | 4528 | 332300.864
32 | Plastering 20mm thick with cement mortar (1:3) on Masonry work in sub structure as per technical specifications.
32.01 | Syphon | sqm. | 83.52 | 139 | 11609.28
32.02 | VCW | sqm. | 161.69 | 139 | 22474.91
33 | Structural cement concrete (Design Mix) in open foundations, with form work, at any level. Cement concrete for plain/reinforced concrete in open foundations as per drawing and technical specification. [MoRTH Specification : Section 1700 & 1500]. With 20mm nominal size aggregate P.C.C. M-15 grade
33.01 | RCC Bridge | cum | 272.8 | 3590 | 979352
34 | Structural cement concrete for plain concrete/ reinforced concrete for substructure at any level, complete as per drawing and technical specification. Design mix concrete – [MoRTH Specification : Section 1500 & 1700]. PCC M-25 grade Upto 5 mtr. Height
34.01 | RCC Bridge | cum | 414.37 | 3915 | 1622258.55
35 | Providing A.C. pipe Weep holes 150mm dia in Masonry/plain Concrete/Reinforced Concrete abutment, wing wall/return wall complete as per drawing and technical specification. [MoRTH Specification : Clause 2205].
35.01 | Retaining wall | R.Mtr. | 120 | 114 | 13680
35.02 | RCC Bridge | R.Mtr. | 420 | 114 | 47880
36 | Steel reinforcement in substructure complete. [MoRTH Specification : Section 1600] HYSD reinforcement
36.01 | RCC Bridge | Tonne | 64.55 | 88737 | 5727973.35
36.02 | VCW | Tonne | 4.403 | 88737 | 390709.011
37 | Providing and laying steel reinforcement at any level in foundation complete as per drawing and technical specification. [MoRTH Specification : Section 1600]. HYSD bar reinforcement
37.01 | RCC Bridge | Tonne | 57.16 | 88567 | 5062489.72
38 | Structural RCC/PSC upto a height of 5 mtr. for reinforced concrete in superstructure complete including steel formwork, scaffolding etc. As per drawing and technical specification.Design mix concrete. [MoRTH Specification : 1500 & 1700].RCC M-30 grade Solid slab superstructure
38.01 | RCC Bridge | cum | 297.09 | 6307 | 1873746.63
39 | Reinforced cement concrete wearing coat M-30 grade at any level including formwork and reinforcement complete as per drawing and technical Specification. [MoRTH Specification : Clause 2204, 1500 & 1700].
39.01 | RCC Bridge | cum | 43.56 | 7720 | 336283.2
40 | Providing and Laying PCC M-15 grade leveling course below approach slab complete as per drawing and technical specifications. [MoRTH specification : 2700]
40.01 | RCC Bridge | cum | 14.22 | 2471 | 35137.62
41 | Reinforced cement concrete M-30 grade approach slab including reinforcement and formwork complete as per drawing and technical specifications. [MoRTH specification : 1500, 1600, 1700, 2704]
41.01 | RCC Bridge | cum | 21.33 | 7073 | 150867.09
42 | Providing and laying HYSD bar reinforcement at any level in superstructure complete as per drawing and technical Specification. [MoRTH Specification : Section 1600]
42.01 | RCC Bridge | Tonne | 27.07 | 89654 | 2426933.78
43 | Providing and filling in foundation trenches, and back filling behind abutments, wing walls, return wall etc., and below pipe bed in layers not exceeding 150mm thick including watering and compacting (IRC-78) complete as per drawing and technical specifications (MoRTH specification 710 & 2200) including all lead and lifts. Selected granular Material in filling (MoRTH specification : Clause 2200).
43.01 | RCC Bridge | cum | 246.32 | 745 | 183508.4
44 | Filter medium behind abutment, wing wall and return wall, complete as per drawing and technical specification. (Same as R7.20.3) [MoRTH Specification : Clause 2504].
44.01 | RCC Bridge | cum | 419.13 | 560 | 234712.8
45 | Providing, laying and fixing of Filler Joint Providing and fixing 2mm thick Corrugated Copper Plate in expansion joint complete as per drawing and technical specifications in MoRTH specification : clause 2605.
45.01 | RCC Bridge | Mtr | 25.5 | 3673 | 93661.5
46 | Supply of flood gauge (water gauge) as per IRC 67 standard 200cm long fixed on angle iron posts 50×50×6mm 2.6m long
46.01 | RCC Bridge | Nos | 2 | 1383 | 2766
47 | Providing and Laying un-reinforced, dowel jointed, plain cement concrete pavement over a prepared sub-base with 43 grade cement, coarse and fine aggregate conforming to IS:383, maximum size of coarse aggregate not exceeding 25mm, mixed in a batching and mixing plant as per approved mix design, transported to site, laid with a fixed form or slip form paver, spread, compacted and finished in a continuous operation including provision of contraction, expansion, construction and longitudinal joints, joint filler, separation membrane, sealant primer, joint sealant, debonding strip, dowel bar, tie rod, admixtures and vacuum processing pump as approved, curing compound, finishing to lines and grades as per drawing as per MoRTH Specification : Clause No. 602, 112.Using Cement concrete M-20 pavement Grade
47.01 | RCC Bridge | cum | 34.425 | 4747 | 163415.475
48 | Providing and laying graded stone aggregate filter Material underneath pitching on slopes complete as per drawing and technical specification. (MoRTH specification : clause 2504).
48.01 | VCW | Cum | 139.32 | 942 | 131239.44
| Total |  |  |  | 52136454.936
| Add Tender Premium | % | 9.05 | Below | -4718349
| Grand Total |  |  |  | 47418105.936
Prit

## Extra Items
EXTRA ITEM SLIP
Name of Work :- |  | Construction of Aamli Fala Bridge and Kherveda Nai Basti to Veeri Border Via Kuniya Vali Mata Road
Name of Contractor or supplier : |  | M/s. Shri Bajrang Construction, Padli Gujareshwar, Dungarpur
Reference to work order or Agreement : |  | 1909 Dt. 17-07-2023
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-01 |  |  | 0 | Each | 5075 | 0
E-02 |  |  | 0 | Each | 107 | 0
E-03 |  |  | 0 | Each | 176 | 0
E-04 |  |  | 0 | Each | 345 | 0
E-05 |  |  | 0 | Each | 107 | 0
E-06 |  |  | 0 | Each | 176 | 0
|  | Total |  |  |  | 0
|  | Add Tender Premium | % | 9.05 | Below | 0
|  | Grand Total |  |  |  | 0