## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-002/2025-26
Agreement No. | 66/2025-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 772628
Date of written order to commence work | 15-01-2025
St. Date of Completion | 04-09-2025
Date of actual completion of work
Tender Premium % | 12.79
Premium Type | Below

## Work Order
Agreement No. | 66/2025-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 772628
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing aluminium partition | sqm | 143.83 | 2400 | 345192
2 | Brick masonry in CM 1:6 | cum | 83.59 | 3200 | 267488
3 | Providing and laying vitrified tiles 600x600 | sqm | 133.35 | 920 | 122682
4 | Providing and fixing MS grill | sqm | 98.05 | 1200 | 117660
5 | Earthwork excavation in ordinary soil | cum | 53.67 | 45 | 2415.15

## Bill Quantity
Agreement No. | 66/2025-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing aluminium partition | sqm | 96.04 | 189.77 | 2400
2 | Brick masonry in CM 1:6 | cum | 118.94 | 145.94 | 3200
3 | Providing and laying vitrified tiles 600x600 | sqm | 110.89 | 173.96 | 920
4 | Providing and fixing MS grill | sqm | 17.53 | 40.5 | 1200
5 | Earthwork excavation in ordinary soil | cum | 99.03 | 102.64 | 45

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.