## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-003/2025-26
Agreement No. | 91/2024-26
Name of Work | Providing Street Lighting in Residential Colony
Name of Contractor or supplier | M/s. Shivshakti Traders, Jodhpur
Work Order Amount Rs. | 2550349
Date of written order to commence work | 10-01-2025
St. Date of Completion | 05-09-2025
Date of actual completion of work
Tender Premium % | 0.29
Premium Type | Above

## Work Order
Agreement No. | 91/2024-26
Name of Work | Providing Street Lighting in Residential Colony
Name of Contractor or supplier | M/s. Shivshakti Traders, Jodhpur
Work Order Amount Rs. | 2550349
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing MS door frame | each | 128.6 | 2800 | 360080
2 | Providing and fixing aluminium partition | sqm | 163.72 | 2400 | 392928
3 | Earthwork excavation in ordinary soil | cum | 81.46 | 45 | 3665.7
4 | Painting with OBD two coats | sqm | 184.62 | 95 | 17538.9
5 | Providing and laying IPS flooring | sqm | 152.78 | 280 | 42778.4
6 | Providing and laying DPC 40mm thick | sqm | 164.7 | 320 | 52704
7 | Providing and fixing flush door shutter | sqm | 16.56 | 1450 | 24012
8 | Providing and laying RCC M20 | cum | 166.38 | 6800 | 1131384
9 | Providing and laying PCC 1:4:8 | cum | 191.32 | 4200 | 803544

## Bill Quantity
Agreement No. | 91/2024-26
Name of Work | Providing Street Lighting in Residential Colony
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing MS door frame | each | 91.07 | 149.05 | 2800
2 | Providing and fixing aluminium partition | sqm | 62.42 | 127.45 | 2400
3 | Earthwork excavation in ordinary soil | cum | 43.76 | 47.32 | 45
4 | Painting with OBD two coats | sqm | 120.41 | 131.85 | 95
5 | Providing and laying IPS flooring | sqm | 32.39 | 55.24 | 280
6 | Providing and laying DPC 40mm thick | sqm | 66.13 | 165.97 | 320
7 | Providing and fixing flush door shutter | sqm | 67.36 | 109 | 1450
8 | Providing and laying RCC M20 | cum | 45.92 | 55.52 | 6800
9 | Providing and laying PCC 1:4:8 | cum | 78.53 | 135.1 | 4200

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.