## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-005/2025-26
Agreement No. | 57/2024-26
Name of Work | Repair and Renovation of Government School Building
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1450273
Date of written order to commence work | 20-04-2025
St. Date of Completion | 23-12-2025
Date of actual completion of work
Tender Premium % | 5.55
Premium Type | Above

## Work Order
Agreement No. | 57/2024-26
Name of Work | Repair and Renovation of Government School Building
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1450273
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and laying DPC 40mm thick | sqm | 80.99 | 320 | 25916.8
2 | Providing and fixing ceramic tiles 300x300 | sqm | 73.78 | 680 | 50170.4
3 | Painting with OBD two coats | sqm | 44.69 | 95 | 4245.55
4 | Plastering 12mm thick CM 1:6 | sqm | 25.22 | 185 | 4665.7
5 | Providing and fixing UPVC window | sqm | 11.44 | 1850 | 21164
6 | Providing and fixing flush door shutter | sqm | 155.78 | 1450 | 225881
7 | Brick masonry in CM 1:6 | cum | 179.13 | 3200 | 573216
8 | Providing and laying PCC 1:4:8 | cum | 188.98 | 4200 | 793716

## Bill Quantity
Agreement No. | 57/2024-26
Name of Work | Repair and Renovation of Government School Building
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and laying DPC 40mm thick | sqm | 134.97 | 147.06 | 320
2 | Providing and fixing ceramic tiles 300x300 | sqm | 78.62 | 123.96 | 680
3 | Painting with OBD two coats | sqm | 130.45 | 189.97 | 95
4 | Plastering 12mm thick CM 1:6 | sqm | 30.51 | 43.49 | 185
5 | Providing and fixing UPVC window | sqm | 145.72 | 176.02 | 1850
6 | Providing and fixing flush door shutter | sqm | 89.7 | 110.04 | 1450
7 | Brick masonry in CM 1:6 | cum | 48.5 | 62.65 | 3200
8 | Providing and laying PCC 1:4:8 | cum | 43.09 | 125.82 | 4200

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.