## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-006/2025-26
Agreement No. | 25/2024-25
Name of Work | Construction of Community Hall at Village Rampur
Name of Contractor or supplier | M/s. Krishna Enterprises, Kota
Work Order Amount Rs. | 1517636
Date of written order to commence work | 06-01-2025
St. Date of Completion | 07-04-2025
Date of actual completion of work
Tender Premium % | 8.34
Premium Type | Above

## Work Order
Agreement No. | 25/2024-25
Name of Work | Construction of Community Hall at Village Rampur
Name of Contractor or supplier | M/s. Krishna Enterprises, Kota
Work Order Amount Rs. | 1517636
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing MS door frame | each | 98.34 | 2800 | 275352
2 | Providing and fixing UPVC window | sqm | 10.3 | 1850 | 19055
3 | Painting with OBD two coats | sqm | 105.22 | 95 | 9995.9
4 | Providing and laying RCC M20 | cum | 87.63 | 6800 | 595884
5 | Providing and fixing ceramic tiles 300x300 | sqm | 166.09 | 680 | 112941.2
6 | Providing and laying PCC 1:4:8 | cum | 139.59 | 4200 | 586278
7 | Providing and fixing flush door shutter | sqm | 22.35 | 1450 | 32407.5

## Bill Quantity
Agreement No. | 25/2024-25
Name of Work | Construction of Community Hall at Village Rampur
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing MS door frame | each | 49.34 | 71.38 | 2800
2 | Providing and fixing UPVC window | sqm | 12.2 | 14.41 | 1850
3 | Painting with OBD two coats | sqm | 60.25 | 189.61 | 95
4 | Providing and laying RCC M20 | cum | 153.15 | 164.38 | 6800
5 | Providing and fixing ceramic tiles 300x300 | sqm | 85.7 | 141.01 | 680
6 | Providing and laying PCC 1:4:8 | cum | 48.52 | 130.96 | 4200
7 | Providing and fixing flush door shutter | sqm | 170.1 | 199.51 | 1450

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.