## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-007/2025-26
Agreement No. | 32/2025-26
Name of Work | Renovation of Police Station Building
Name of Contractor or supplier | M/s. Shivshakti Traders, Jodhpur
Work Order Amount Rs. | 772049
Date of written order to commence work | 21-03-2025
St. Date of Completion | 13-11-2025
Date of actual completion of work
Tender Premium % | 10.57
Premium Type | Above

## Work Order
Agreement No. | 32/2025-26
Name of Work | Renovation of Police Station Building
Name of Contractor or supplier | M/s. Shivshakti Traders, Jodhpur
Work Order Amount Rs. | 772049
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing aluminium partition | sqm | 26.99 | 2400 | 64776
2 | Brick masonry in CM 1:6 | cum | 109.99 | 3200 | 351968
3 | Painting with OBD two coats | sqm | 21.53 | 95 | 2045.35
4 | Providing and laying vitrified tiles 600x600 | sqm | 114.99 | 920 | 105790.8
5 | Providing and laying IPS flooring | sqm | 168.86 | 280 | 47280.8
6 | Providing and laying DPC 40mm thick | sqm | 177.45 | 320 | 56784

## Bill Quantity
Agreement No. | 32/2025-26
Name of Work | Renovation of Police Station Building
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing aluminium partition | sqm | 70.83 | 117.65 | 2400
2 | Brick masonry in CM 1:6 | cum | 71.52 | 99.41 | 3200
3 | Painting with OBD two coats | sqm | 69.41 | 166.63 | 95
4 | Providing and laying vitrified tiles 600x600 | sqm | 160.47 | 175.8 | 920
5 | Providing and laying IPS flooring | sqm | 63.64 | 82.1 | 280
6 | Providing and laying DPC 40mm thick | sqm | 71.13 | 90.02 | 320

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.