## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-008/2025-26
Agreement No. | 10/2024-25
Name of Work | Construction of Boundary Wall at District Hospital
Name of Contractor or supplier | M/s. Rajputana Constructions, Ajmer
Work Order Amount Rs. | 1216731
Date of written order to commence work | 24-02-2025
St. Date of Completion | 14-07-2025
Date of actual completion of work
Tender Premium % | 2.28
Premium Type | Above

## Work Order
Agreement No. | 10/2024-25
Name of Work | Construction of Boundary Wall at District Hospital
Name of Contractor or supplier | M/s. Rajputana Constructions, Ajmer
Work Order Amount Rs. | 1216731
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Painting with OBD two coats | sqm | 122.88 | 95 | 11673.6
2 | Providing and fixing ceramic tiles 300x300 | sqm | 91.88 | 680 | 62478.4
3 | Earthwork excavation in ordinary soil | cum | 157.2 | 45 | 7074
4 | Providing and fixing aluminium partition | sqm | 135.46 | 2400 | 325104
5 | Providing and laying vitrified tiles 600x600 | sqm | 63.68 | 920 | 58585.6
6 | Providing and laying DPC 40mm thick | sqm | 10 | 320 | 3200
7 | Providing and fixing MS door frame | each | 120.1 | 2800 | 336280
8 | Providing and fixing MS grill | sqm | 101.52 | 1200 | 121824
9 | Brick masonry in CM 1:6 | cum | 126.29 | 3200 | 404128
10 | Providing and laying PCC 1:4:8 | cum | 173.09 | 4200 | 726978

## Bill Quantity
Agreement No. | 10/2024-25
Name of Work | Construction of Boundary Wall at District Hospital
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Painting with OBD two coats | sqm | 54.71 | 92.6 | 95
2 | Providing and fixing ceramic tiles 300x300 | sqm | 24.38 | 36.86 | 680
3 | Earthwork excavation in ordinary soil | cum | 61.87 | 107.26 | 45
4 | Providing and fixing aluminium partition | sqm | 83.15 | 137.38 | 2400
5 | Providing and laying vitrified tiles 600x600 | sqm | 115.9 | 118.28 | 920
6 | Providing and laying DPC 40mm thick | sqm | 55.69 | 84.35 | 320
7 | Providing and fixing MS door frame | each | 82.89 | 100.76 | 2800
8 | Providing and fixing MS grill | sqm | 122.37 | 130.04 | 1200
9 | Brick masonry in CM 1:6 | cum | 51.38 | 78.51 | 3200
10 | Providing and laying PCC 1:4:8 | cum | 57.75 | 176.93 | 4200

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.