## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-009/2025-26
Agreement No. | 81/2025-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1021910
Date of written order to commence work | 07-06-2025
St. Date of Completion | 15-10-2025
Date of actual completion of work
Tender Premium % | 1.84
Premium Type | Below

## Work Order
Agreement No. | 81/2025-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1021910
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Brick masonry in CM 1:6 | cum | 79.04 | 3200 | 252928
2 | Providing and fixing MS door frame | each | 83.75 | 2800 | 234500
3 | Providing and fixing MS grill | sqm | 184.95 | 1200 | 221940
4 | Providing and laying PCC 1:4:8 | cum | 124.81 | 4200 | 524202
5 | Providing and fixing UPVC window | sqm | 97.3 | 1850 | 180005
6 | Providing and laying vitrified tiles 600x600 | sqm | 131.52 | 920 | 120998.4
7 | Providing and fixing aluminium partition | sqm | 173.93 | 2400 | 417432
8 | Providing and laying IPS flooring | sqm | 73.04 | 280 | 20451.2
9 | Earthwork excavation in ordinary soil | cum | 103.36 | 45 | 4651.2

## Bill Quantity
Agreement No. | 81/2025-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Brick masonry in CM 1:6 | cum | 149.43 | 180.24 | 3200
2 | Providing and fixing MS door frame | each | 42.29 | 125.16 | 2800
3 | Providing and fixing MS grill | sqm | 40.81 | 90.24 | 1200
4 | Providing and laying PCC 1:4:8 | cum | 7.34 | 13.91 | 4200
5 | Providing and fixing UPVC window | sqm | 25.95 | 48.55 | 1850
6 | Providing and laying vitrified tiles 600x600 | sqm | 44.03 | 123.13 | 920
7 | Providing and fixing aluminium partition | sqm | 19.31 | 25.1 | 2400
8 | Providing and laying IPS flooring | sqm | 10.81 | 27.86 | 280
9 | Earthwork excavation in ordinary soil | cum | 60.84 | 159.11 | 45

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.