## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-012/2025-26
Agreement No. | 76/2024-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 2151369
Date of written order to commence work | 09-01-2025
St. Date of Completion | 27-11-2025
Date of actual completion of work
Tender Premium % | 2.88
Premium Type | Above

## Work Order
Agreement No. | 76/2024-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 2151369
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing ceramic tiles 300x300 | sqm | 92.99 | 680 | 63233.2
2 | Providing and fixing MS door frame | each | 42.86 | 2800 | 120008
3 | Providing and laying PCC 1:4:8 | cum | 46.42 | 4200 | 194964
4 | Providing and fixing UPVC window | sqm | 174.38 | 1850 | 322603
5 | Providing and laying vitrified tiles 600x600 | sqm | 56.25 | 920 | 51750
6 | Providing and fixing MS grill | sqm | 49.69 | 1200 | 59628
7 | Brick masonry in CM 1:6 | cum | 192.74 | 3200 | 616768

## Bill Quantity
Agreement No. | 76/2024-25
Name of Work | Repair of Road from Main Market to Bus Stand
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing ceramic tiles 300x300 | sqm | 97.4 | 101.33 | 680
2 | Providing and fixing MS door frame | each | 113.18 | 120.75 | 2800
3 | Providing and laying PCC 1:4:8 | cum | 27.06 | 34.11 | 4200
4 | Providing and fixing UPVC window | sqm | 80.22 | 170.52 | 1850
5 | Providing and laying vitrified tiles 600x600 | sqm | 55.65 | 180.24 | 920
6 | Providing and fixing MS grill | sqm | 16.92 | 51.31 | 1200
7 | Brick masonry in CM 1:6 | cum | 50.29 | 88.92 | 3200

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.