## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-015/2025-26
Agreement No. | 72/2025-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 1918456
Date of written order to commence work | 01-03-2025
St. Date of Completion | 08-07-2025
Date of actual completion of work
Tender Premium % | 13.74
Premium Type | Above

## Work Order
Agreement No. | 72/2025-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 1918456
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Earthwork excavation in ordinary soil | cum | 168.63 | 45 | 7588.35
2 | Providing and fixing MS grill | sqm | 180.67 | 1200 | 216804
3 | Providing and fixing flush door shutter | sqm | 106.21 | 1450 | 154004.5
4 | Providing and fixing MS door frame | each | 197.95 | 2800 | 554260
5 | Providing and laying PCC 1:4:8 | cum | 94.86 | 4200 | 398412
6 | Providing and laying vitrified tiles 600x600 | sqm | 70.64 | 920 | 64988.8
7 | Providing and fixing ceramic tiles 300x300 | sqm | 79.1 | 680 | 53788

## Bill Quantity
Agreement No. | 72/2025-25
Name of Work | Repair of Road from Main Market to Bus Stand
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Earthwork excavation in ordinary soil | cum | 138.73 | 161.89 | 45
2 | Providing and fixing MS grill | sqm | 40.33 | 41.9 | 1200
3 | Providing and fixing flush door shutter | sqm | 122.15 | 191.16 | 1450
4 | Providing and fixing MS door frame | each | 27.16 | 74.5 | 2800
5 | Providing and laying PCC 1:4:8 | cum | 61.51 | 157.27 | 4200
6 | Providing and laying vitrified tiles 600x600 | sqm | 13.74 | 23.35 | 920
7 | Providing and fixing ceramic tiles 300x300 | sqm | 88.54 | 195.84 | 680

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier : | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Reference to work order or Agreement : | 72/2025-25
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-03 | 10.3.1 | Providing and fixing MCB 32A | 2 | Each | 480 | 960 | Approved
E-06 | 12.1.1 | Providing and fixing exhaust fan 300mm | 2 | Each | 1200 | 2400 | Approved
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
E-05 | 11.2.1 | Providing and fixing ball valve 25mm | 3 | Each | 420 | 1260 | Approved
| Total |  |  |  |  | 6320