## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-016/2025-26
Agreement No. | 48/2025-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1926208
Date of written order to commence work | 16-05-2025
St. Date of Completion | 02-01-2026
Date of actual completion of work
Tender Premium % | 3.93
Premium Type | Below

## Work Order
Agreement No. | 48/2025-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1926208
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing MS door frame | each | 119.52 | 2800 | 334656
2 | Providing and laying DPC 40mm thick | sqm | 161.58 | 320 | 51705.6
3 | Providing and laying RCC M20 | cum | 196.79 | 6800 | 1338172
4 | Providing and laying vitrified tiles 600x600 | sqm | 185.38 | 920 | 170549.6
5 | Providing and fixing flush door shutter | sqm | 61.13 | 1450 | 88638.5

## Bill Quantity
Agreement No. | 48/2025-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing MS door frame | each | 9.36 | 15.56 | 2800
2 | Providing and laying DPC 40mm thick | sqm | 111.64 | 156.36 | 320
3 | Providing and laying RCC M20 | cum | 22.55 | 29.05 | 6800
4 | Providing and laying vitrified tiles 600x600 | sqm | 184.19 | 188.63 | 920
5 | Providing and fixing flush door shutter | sqm | 90.31 | 133.54 | 1450

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier : | M/s. Bajrang Builders, Udaipur
Reference to work order or Agreement : | 48/2025-25
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-04 | 11.1.2 | Providing and fixing CPVC pipe 25mm | 15 | Rmt | 185 | 2775 | Approved
E-05 | 11.2.1 | Providing and fixing ball valve 25mm | 3 | Each | 420 | 1260 | Approved
| Total |  |  |  |  | 4035