## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-017/2025-26
Agreement No. | 88/2024-26
Name of Work | Construction of Anganwadi Centre at Village Khera
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 1812193
Date of written order to commence work | 04-06-2025
St. Date of Completion | 06-12-2025
Date of actual completion of work
Tender Premium % | 2.62
Premium Type | Below

## Work Order
Agreement No. | 88/2024-26
Name of Work | Construction of Anganwadi Centre at Village Khera
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 1812193
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and laying RCC M20 | cum | 26.96 | 6800 | 183328
2 | Painting with OBD two coats | sqm | 113.15 | 95 | 10749.25
3 | Providing and fixing flush door shutter | sqm | 169.05 | 1450 | 245122.5
4 | Providing and fixing UPVC window | sqm | 132.87 | 1850 | 245809.5
5 | Providing and fixing aluminium partition | sqm | 185.8 | 2400 | 445920
6 | Earthwork excavation in ordinary soil | cum | 67.83 | 45 | 3052.35
7 | Providing and laying vitrified tiles 600x600 | sqm | 192.76 | 920 | 177339.2
8 | Providing and fixing MS grill | sqm | 80.98 | 1200 | 97176

## Bill Quantity
Agreement No. | 88/2024-26
Name of Work | Construction of Anganwadi Centre at Village Khera
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and laying RCC M20 | cum | 9.8 | 29.02 | 6800
2 | Painting with OBD two coats | sqm | 9.98 | 21.26 | 95
3 | Providing and fixing flush door shutter | sqm | 17.92 | 39.01 | 1450
4 | Providing and fixing UPVC window | sqm | 75.53 | 99.26 | 1850
5 | Providing and fixing aluminium partition | sqm | 96.75 | 181.48 | 2400
6 | Earthwork excavation in ordinary soil | cum | 172.78 | 181.86 | 45
7 | Providing and laying vitrified tiles 600x600 | sqm | 49.42 | 90.58 | 920
8 | Providing and fixing MS grill | sqm | 86.53 | 120.61 | 1200

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Construction of Anganwadi Centre at Village Khera
Name of Contractor or supplier : | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Reference to work order or Agreement : | 88/2024-26
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-04 | 11.1.2 | Providing and fixing CPVC pipe 25mm | 15 | Rmt | 185 | 2775 | Approved
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
E-03 | 10.3.1 | Providing and fixing MCB 32A | 2 | Each | 480 | 960 | Approved
E-06 | 12.1.1 | Providing and fixing exhaust fan 300mm | 2 | Each | 1200 | 2400 | Approved
E-05 | 11.2.1 | Providing and fixing ball valve 25mm | 3 | Each | 420 | 1260 | Approved
| Total |  |  |  |  | 9095