## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-018/2025-26
Agreement No. | 12/2025-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Rajputana Constructions, Ajmer
Work Order Amount Rs. | 1135610
Date of written order to commence work | 15-01-2025
St. Date of Completion | 08-09-2025
Date of actual completion of work
Tender Premium % | 2.18
Premium Type | Above

## Work Order
Agreement No. | 12/2025-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Rajputana Constructions, Ajmer
Work Order Amount Rs. | 1135610
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing ceramic tiles 300x300 | sqm | 70.02 | 680 | 47613.6
2 | Earthwork excavation in ordinary soil | cum | 45.32 | 45 | 2039.4
3 | Providing and laying RCC M20 | cum | 34.92 | 6800 | 237456
4 | Providing and fixing MS door frame | each | 67.05 | 2800 | 187740
5 | Providing and laying vitrified tiles 600x600 | sqm | 128.08 | 920 | 117833.6
6 | Providing and fixing aluminium partition | sqm | 112.25 | 2400 | 269400
7 | Plastering 12mm thick CM 1:6 | sqm | 180.82 | 185 | 33451.7

## Bill Quantity
Agreement No. | 12/2025-25
Name of Work | Repair of Road from Main Market to Bus Stand
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing ceramic tiles 300x300 | sqm | 29.64 | 35.7 | 680
2 | Earthwork excavation in ordinary soil | cum | 77.48 | 154.73 | 45
3 | Providing and laying RCC M20 | cum | 36.62 | 51.1 | 6800
4 | Providing and fixing MS door frame | each | 21.19 | 50 | 2800
5 | Providing and laying vitrified tiles 600x600 | sqm | 53.87 | 101.66 | 920
6 | Providing and fixing aluminium partition | sqm | 13.3 | 24.27 | 2400
7 | Plastering 12mm thick CM 1:6 | sqm | 25.61 | 30.43 | 185

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier : | M/s. Rajputana Constructions, Ajmer
Reference to work order or Agreement : | 12/2025-25
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-03 | 10.3.1 | Providing and fixing MCB 32A | 2 | Each | 480 | 960 | Approved
E-04 | 11.1.2 | Providing and fixing CPVC pipe 25mm | 15 | Rmt | 185 | 2775 | Approved
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
| Total |  |  |  |  | 5435