## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-020/2025-26
Agreement No. | 34/2024-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 1857684
Date of written order to commence work | 20-01-2025
St. Date of Completion | 02-12-2025
Date of actual completion of work
Tender Premium % | 14.12
Premium Type | Below

## Work Order
Agreement No. | 34/2024-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 1857684
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Earthwork excavation in ordinary soil | cum | 141.97 | 45 | 6388.65
2 | Providing and fixing MS grill | sqm | 31.48 | 1200 | 37776
3 | Painting with OBD two coats | sqm | 186.25 | 95 | 17693.75
4 | Plastering 12mm thick CM 1:6 | sqm | 149.84 | 185 | 27720.4
5 | Providing and laying RCC M20 | cum | 110.8 | 6800 | 753440
6 | Providing and fixing ceramic tiles 300x300 | sqm | 63.7 | 680 | 43316
7 | Providing and fixing UPVC window | sqm | 89.49 | 1850 | 165556.5
8 | Providing and fixing flush door shutter | sqm | 74.43 | 1450 | 107923.5

## Bill Quantity
Agreement No. | 34/2024-25
Name of Work | Providing and Fixing of Water Supply Pipeline
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Earthwork excavation in ordinary soil | cum | 25.28 | 43.95 | 45
2 | Providing and fixing MS grill | sqm | 41.99 | 127.17 | 1200
3 | Painting with OBD two coats | sqm | 7.85 | 20.92 | 95
4 | Plastering 12mm thick CM 1:6 | sqm | 155.35 | 182.09 | 185
5 | Providing and laying RCC M20 | cum | 123.57 | 124.2 | 6800
6 | Providing and fixing ceramic tiles 300x300 | sqm | 6.8 | 17.55 | 680
7 | Providing and fixing UPVC window | sqm | 39.5 | 88.74 | 1850
8 | Providing and fixing flush door shutter | sqm | 107.56 | 112.91 | 1450

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Providing and Fixing of Water Supply Pipeline
Name of Contractor or supplier : | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Reference to work order or Agreement : | 34/2024-25
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
E-02 | 10.2.3 | Providing and fixing 6A 3-pin socket | 4 | Each | 320 | 1280 | Approved
| Total |  |  |  |  | 2980