## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-021/2025-26
Agreement No. | 58/2025-26
Name of Work | Renovation of PHC Building at Tehsil Headquarters
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 1567178
Date of written order to commence work | 12-06-2025
St. Date of Completion | 23-09-2025
Date of actual completion of work
Tender Premium % | 14.58
Premium Type | Below

## Work Order
Agreement No. | 58/2025-26
Name of Work | Renovation of PHC Building at Tehsil Headquarters
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 1567178
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Painting with OBD two coats | sqm | 136.73 | 95 | 12989.35
2 | Providing and laying PCC 1:4:8 | cum | 103.91 | 4200 | 436422
3 | Providing and fixing aluminium partition | sqm | 161.18 | 2400 | 386832
4 | Providing and laying IPS flooring | sqm | 115.07 | 280 | 32219.6
5 | Providing and laying DPC 40mm thick | sqm | 102.97 | 320 | 32950.4
6 | Providing and fixing flush door shutter | sqm | 100.31 | 1450 | 145449.5
7 | Providing and fixing MS door frame | each | 191.73 | 2800 | 536844

## Bill Quantity
Agreement No. | 58/2025-26
Name of Work | Renovation of PHC Building at Tehsil Headquarters
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Painting with OBD two coats | sqm | 94.84 | 120.35 | 95
2 | Providing and laying PCC 1:4:8 | cum | 85.68 | 134.07 | 4200
3 | Providing and fixing aluminium partition | sqm | 48.24 | 75.44 | 2400
4 | Providing and laying IPS flooring | sqm | 9.82 | 22.37 | 280
5 | Providing and laying DPC 40mm thick | sqm | 27.11 | 44.99 | 320
6 | Providing and fixing flush door shutter | sqm | 58.77 | 104.35 | 1450
7 | Providing and fixing MS door frame | each | 57.13 | 143.96 | 2800

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Renovation of PHC Building at Tehsil Headquarters
Name of Contractor or supplier : | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Reference to work order or Agreement : | 58/2025-26
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-04 | 11.1.2 | Providing and fixing CPVC pipe 25mm | 15 | Rmt | 185 | 2775 | Approved
E-06 | 12.1.1 | Providing and fixing exhaust fan 300mm | 2 | Each | 1200 | 2400 | Approved
E-02 | 10.2.3 | Providing and fixing 6A 3-pin socket | 4 | Each | 320 | 1280 | Approved
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
E-03 | 10.3.1 | Providing and fixing MCB 32A | 2 | Each | 480 | 960 | Approved
E-05 | 11.2.1 | Providing and fixing ball valve 25mm | 3 | Each | 420 | 1260 | Approved
| Total |  |  |  |  | 10375