## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-022/2025-26
Agreement No. | 83/2024-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 884795
Date of written order to commence work | 01-03-2025
St. Date of Completion | 30-11-2025
Date of actual completion of work
Tender Premium % | 0.18
Premium Type | Above

## Work Order
Agreement No. | 83/2024-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 884795
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and laying PCC 1:4:8 | cum | 62.62 | 4200 | 263004
2 | Providing and fixing MS grill | sqm | 107.52 | 1200 | 129024
3 | Providing and fixing flush door shutter | sqm | 131.06 | 1450 | 190037
4 | Providing and laying DPC 40mm thick | sqm | 155.48 | 320 | 49753.6
5 | Providing and laying vitrified tiles 600x600 | sqm | 33.04 | 920 | 30396.8
6 | Painting with OBD two coats | sqm | 138.8 | 95 | 13186
7 | Brick masonry in CM 1:6 | cum | 74.38 | 3200 | 238016

## Bill Quantity
Agreement No. | 83/2024-25
Name of Work | Repair of Road from Main Market to Bus Stand
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and laying PCC 1:4:8 | cum | 31.54 | 39.56 | 4200
2 | Providing and fixing MS grill | sqm | 157.28 | 185.29 | 1200
3 | Providing and fixing flush door shutter | sqm | 60.66 | 193.54 | 1450
4 | Providing and laying DPC 40mm thick | sqm | 29.48 | 85.56 | 320
5 | Providing and laying vitrified tiles 600x600 | sqm | 25.44 | 68.25 | 920
6 | Painting with OBD two coats | sqm | 78.02 | 189.24 | 95
7 | Brick masonry in CM 1:6 | cum | 21.25 | 36.83 | 3200

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier : | M/s. Bajrang Builders, Udaipur
Reference to work order or Agreement : | 83/2024-25
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-02 | 10.2.3 | Providing and fixing 6A 3-pin socket | 4 | Each | 320 | 1280 | Approved
E-05 | 11.2.1 | Providing and fixing ball valve 25mm | 3 | Each | 420 | 1260 | Approved
E-04 | 11.1.2 | Providing and fixing CPVC pipe 25mm | 15 | Rmt | 185 | 2775 | Approved
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
E-03 | 10.3.1 | Providing and fixing MCB 32A | 2 | Each | 480 | 960 | Approved
| Total |  |  |  |  | 7975