## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-024/2025-26
Agreement No. | 29/2024-25
Name of Work | Renovation of PHC Building at Tehsil Headquarters
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1043711
Date of written order to commence work | 03-04-2025
St. Date of Completion | 12-09-2025
Date of actual completion of work
Tender Premium % | 9.69
Premium Type | Above

## Work Order
Agreement No. | 29/2024-25
Name of Work | Renovation of PHC Building at Tehsil Headquarters
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1043711
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and laying PCC 1:4:8 | cum | 124.47 | 4200 | 522774
2 | Painting with OBD two coats | sqm | 99.17 | 95 | 9421.15
3 | Earthwork excavation in ordinary soil | cum | 157.54 | 45 | 7089.3
4 | Providing and fixing MS grill | sqm | 37.86 | 1200 | 45432
5 | Plastering 12mm thick CM 1:6 | sqm | 43.9 | 185 | 8121.5

## Bill Quantity
Agreement No. | 29/2024-25
Name of Work | Renovation of PHC Building at Tehsil Headquarters
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and laying PCC 1:4:8 | cum | 105.96 | 107.33 | 4200
2 | Painting with OBD two coats | sqm | 91.83 | 145.77 | 95
3 | Earthwork excavation in ordinary soil | cum | 31.72 | 75.65 | 45
4 | Providing and fixing MS grill | sqm | 39.09 | 44.65 | 1200
5 | Plastering 12mm thick CM 1:6 | sqm | 134.4 | 140.2 | 185

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Renovation of PHC Building at Tehsil Headquarters
Name of Contractor or supplier : | M/s. Bajrang Builders, Udaipur
Reference to work order or Agreement : | 29/2024-25
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
E-06 | 12.1.1 | Providing and fixing exhaust fan 300mm | 2 | Each | 1200 | 2400 | Approved
E-02 | 10.2.3 | Providing and fixing 6A 3-pin socket | 4 | Each | 320 | 1280 | Approved
| Total |  |  |  |  | 5380