## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-001/2025-26
Agreement No. | 49/2024-25
Name of Work | Construction of Boundary Wall at District Hospital
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1066467
Date of written order to commence work | 11-02-2025
St. Date of Completion | 06-09-2025
Date of actual completion of work
Tender Premium % | 13.39
Premium Type | Below

## Work Order
Agreement No. | 49/2024-25
Name of Work | Construction of Boundary Wall at District Hospital
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1066467
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Painting with OBD two coats | sqm | 129 | 95 | 12255
2 | Providing and fixing aluminium partition | sqm | 193.03 | 2400 | 463272
3 | Providing and fixing MS grill | sqm | 50.06 | 1200 | 60072
4 | Providing and laying RCC M20 | cum | 191.66 | 6800 | 1303288
5 | Providing and fixing flush door shutter | sqm | 115.53 | 1450 | 167518.5
6 | Providing and fixing MS door frame | each | 181.22 | 2800 | 507416

## Bill Quantity
Agreement No. | 49/2024-25
Name of Work | Construction of Boundary Wall at District Hospital
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Painting with OBD two coats | sqm | 68.2 | 165.42 | 95
2 | Providing and fixing aluminium partition | sqm | 51.54 | 133.22 | 2400
3 | Providing and fixing MS grill | sqm | 6.39 | 11.07 | 1200
4 | Providing and laying RCC M20 | cum | 109.3 | 156.97 | 6800
5 | Providing and fixing flush door shutter | sqm | 41.42 | 46.6 | 1450
6 | Providing and fixing MS door frame | each | 85.58 | 183.62 | 2800

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.