## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-004/2025-26
Agreement No. | 41/2024-26
Name of Work | Construction of Drainage System in Ward No. 5
Name of Contractor or supplier | M/s. Rajputana Constructions, Ajmer
Work Order Amount Rs. | 878955
Date of written order to commence work | 26-02-2025
St. Date of Completion | 18-06-2025
Date of actual completion of work
Tender Premium % | 3.43
Premium Type | Above

## Work Order
Agreement No. | 41/2024-26
Name of Work | Construction of Drainage System in Ward No. 5
Name of Contractor or supplier | M/s. Rajputana Constructions, Ajmer
Work Order Amount Rs. | 878955
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and laying DPC 40mm thick | sqm | 29.52 | 320 | 9446.4
2 | Plastering 12mm thick CM 1:6 | sqm | 27.51 | 185 | 5089.35
3 | Providing and fixing MS grill | sqm | 175.2 | 1200 | 210240
4 | Providing and laying PCC 1:4:8 | cum | 22.47 | 4200 | 94374
5 | Providing and fixing ceramic tiles 300x300 | sqm | 144.97 | 680 | 98579.6
6 | Painting with OBD two coats | sqm | 24.31 | 95 | 2309.45
7 | Providing and fixing UPVC window | sqm | 89.83 | 1850 | 166185.5

## Bill Quantity
Agreement No. | 41/2024-26
Name of Work | Construction of Drainage System in Ward No. 5
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and laying DPC 40mm thick | sqm | 79.45 | 117.91 | 320
2 | Plastering 12mm thick CM 1:6 | sqm | 5.2 | 15.16 | 185
3 | Providing and fixing MS grill | sqm | 20.75 | 53.29 | 1200
4 | Providing and laying PCC 1:4:8 | cum | 24.91 | 70.63 | 4200
5 | Providing and fixing ceramic tiles 300x300 | sqm | 34.54 | 65.29 | 680
6 | Painting with OBD two coats | sqm | 32.81 | 102.23 | 95
7 | Providing and fixing UPVC window | sqm | 21.08 | 55.63 | 1850

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.