## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-010/2025-26
Agreement No. | 96/2025-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 2136693
Date of written order to commence work | 06-04-2025
St. Date of Completion | 25-07-2025
Date of actual completion of work
Tender Premium % | 10.65
Premium Type | Above

## Work Order
Agreement No. | 96/2025-25
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 2136693
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing UPVC window | sqm | 14.43 | 1850 | 26695.5
2 | Providing and fixing MS grill | sqm | 168.37 | 1200 | 202044
3 | Providing and laying PCC 1:4:8 | cum | 99.01 | 4200 | 415842
4 | Providing and fixing flush door shutter | sqm | 164.18 | 1450 | 238061
5 | Providing and fixing MS door frame | each | 189.66 | 2800 | 531048
6 | Providing and laying IPS flooring | sqm | 196.79 | 280 | 55101.2
7 | Painting with OBD two coats | sqm | 43.47 | 95 | 4129.65
8 | Providing and laying RCC M20 | cum | 142.74 | 6800 | 970632

## Bill Quantity
Agreement No. | 96/2025-25
Name of Work | Repair of Road from Main Market to Bus Stand
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing UPVC window | sqm | 12.65 | 30.68 | 1850
2 | Providing and fixing MS grill | sqm | 14.37 | 27.64 | 1200
3 | Providing and laying PCC 1:4:8 | cum | 11.8 | 13.14 | 4200
4 | Providing and fixing flush door shutter | sqm | 55.24 | 65.29 | 1450
5 | Providing and fixing MS door frame | each | 49.77 | 114.14 | 2800
6 | Providing and laying IPS flooring | sqm | 34.29 | 65.49 | 280
7 | Painting with OBD two coats | sqm | 62.44 | 135.13 | 95
8 | Providing and laying RCC M20 | cum | 118.34 | 127.69 | 6800

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.