## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-011/2025-26
Agreement No. | 15/2025-25
Name of Work | Construction of Toilet Block at Government College
Name of Contractor or supplier | M/s. Shree Ram Construction Co., Jaipur
Work Order Amount Rs. | 661278
Date of written order to commence work | 25-06-2025
St. Date of Completion | 17-04-2026
Date of actual completion of work
Tender Premium % | 5.51
Premium Type | Below

## Work Order
Agreement No. | 15/2025-25
Name of Work | Construction of Toilet Block at Government College
Name of Contractor or supplier | M/s. Shree Ram Construction Co., Jaipur
Work Order Amount Rs. | 661278
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and laying vitrified tiles 600x600 | sqm | 65.95 | 920 | 60674
2 | Brick masonry in CM 1:6 | cum | 100.75 | 3200 | 322400
3 | Providing and fixing MS grill | sqm | 168.13 | 1200 | 201756
4 | Providing and laying DPC 40mm thick | sqm | 57.67 | 320 | 18454.4
5 | Providing and laying RCC M20 | cum | 34.05 | 6800 | 231540

## Bill Quantity
Agreement No. | 15/2025-25
Name of Work | Construction of Toilet Block at Government College
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and laying vitrified tiles 600x600 | sqm | 92.05 | 100.07 | 920
2 | Brick masonry in CM 1:6 | cum | 92.4 | 182.15 | 3200
3 | Providing and fixing MS grill | sqm | 131.77 | 183.83 | 1200
4 | Providing and laying DPC 40mm thick | sqm | 73.92 | 167.47 | 320
5 | Providing and laying RCC M20 | cum | 8.01 | 12.3 | 6800

## Extra Items
EXTRA ITEM SLIP
No extra items for this bill.