## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-013/2025-26
Agreement No. | 10/2025-26
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1235706
Date of written order to commence work | 12-02-2025
St. Date of Completion | 18-11-2025
Date of actual completion of work
Tender Premium % | 0.63
Premium Type | Below

## Work Order
Agreement No. | 10/2025-26
Name of Work | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1235706
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Plastering 12mm thick CM 1:6 | sqm | 161.82 | 185 | 29936.7
2 | Providing and fixing flush door shutter | sqm | 123 | 1450 | 178350
3 | Earthwork excavation in ordinary soil | cum | 115.39 | 45 | 5192.55
4 | Providing and fixing UPVC window | sqm | 179.86 | 1850 | 332741
5 | Providing and fixing ceramic tiles 300x300 | sqm | 73.13 | 680 | 49728.4
6 | Providing and fixing MS grill | sqm | 32.43 | 1200 | 38916
7 | Providing and fixing MS door frame | each | 69.81 | 2800 | 195468

## Bill Quantity
Agreement No. | 10/2025-26
Name of Work | Repair of Road from Main Market to Bus Stand
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Plastering 12mm thick CM 1:6 | sqm | 12.49 | 35.8 | 185
2 | Providing and fixing flush door shutter | sqm | 69.08 | 76.42 | 1450
3 | Earthwork excavation in ordinary soil | cum | 136.9 | 146.7 | 45
4 | Providing and fixing UPVC window | sqm | 64.2 | 198.93 | 1850
5 | Providing and fixing ceramic tiles 300x300 | sqm | 67.91 | 107.6 | 680
6 | Providing and fixing MS grill | sqm | 35.47 | 52.64 | 1200
7 | Providing and fixing MS door frame | each | 95.21 | 103.96 | 2800

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Repair of Road from Main Market to Bus Stand
Name of Contractor or supplier : | M/s. Bajrang Builders, Udaipur
Reference to work order or Agreement : | 10/2025-26
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-05 | 11.2.1 | Providing and fixing ball valve 25mm | 3 | Each | 420 | 1260 | Approved
E-06 | 12.1.1 | Providing and fixing exhaust fan 300mm | 2 | Each | 1200 | 2400 | Approved
E-02 | 10.2.3 | Providing and fixing 6A 3-pin socket | 4 | Each | 320 | 1280 | Approved
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
E-04 | 11.1.2 | Providing and fixing CPVC pipe 25mm | 15 | Rmt | 185 | 2775 | Approved
E-03 | 10.3.1 | Providing and fixing MCB 32A | 2 | Each | 480 | 960 | Approved
| Total |  |  |  |  | 10375