## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-014/2025-26
Agreement No. | 62/2025-25
Name of Work | Construction of Community Hall at Village Rampur
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1394955
Date of written order to commence work | 17-02-2025
St. Date of Completion | 24-05-2025
Date of actual completion of work
Tender Premium % | 1.72
Premium Type | Below

## Work Order
Agreement No. | 62/2025-25
Name of Work | Construction of Community Hall at Village Rampur
Name of Contractor or supplier | M/s. Bajrang Builders, Udaipur
Work Order Amount Rs. | 1394955
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing UPVC window | sqm | 198.47 | 1850 | 367169.5
2 | Providing and laying DPC 40mm thick | sqm | 36.88 | 320 | 11801.6
3 | Providing and fixing MS door frame | each | 139.92 | 2800 | 391776
4 | Providing and fixing MS grill | sqm | 146.49 | 1200 | 175788
5 | Brick masonry in CM 1:6 | cum | 117.63 | 3200 | 376416
6 | Providing and fixing ceramic tiles 300x300 | sqm | 68.3 | 680 | 46444

## Bill Quantity
Agreement No. | 62/2025-25
Name of Work | Construction of Community Hall at Village Rampur
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing UPVC window | sqm | 65.44 | 195.39 | 1850
2 | Providing and laying DPC 40mm thick | sqm | 59.14 | 59.57 | 320
3 | Providing and fixing MS door frame | each | 56.12 | 65.55 | 2800
4 | Providing and fixing MS grill | sqm | 110.04 | 161.69 | 1200
5 | Brick masonry in CM 1:6 | cum | 14.85 | 30.6 | 3200
6 | Providing and fixing ceramic tiles 300x300 | sqm | 64.65 | 81.82 | 680

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Construction of Community Hall at Village Rampur
Name of Contractor or supplier : | M/s. Bajrang Builders, Udaipur
Reference to work order or Agreement : | 62/2025-25
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
E-05 | 11.2.1 | Providing and fixing ball valve 25mm | 3 | Each | 420 | 1260 | Approved
E-02 | 10.2.3 | Providing and fixing 6A 3-pin socket | 4 | Each | 320 | 1280 | Approved
| Total |  |  |  |  | 4240