## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-019/2025-26
Agreement No. | 59/2025-25
Name of Work | Construction of Toilet Block at Government College
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 2275699
Date of written order to commence work | 20-03-2025
St. Date of Completion | 26-10-2025
Date of actual completion of work
Tender Premium % | 9.8
Premium Type | Below

## Work Order
Agreement No. | 59/2025-25
Name of Work | Construction of Toilet Block at Government College
Name of Contractor or supplier | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Work Order Amount Rs. | 2275699
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing MS door frame | each | 97.79 | 2800 | 273812
2 | Providing and laying RCC M20 | cum | 77.41 | 6800 | 526388
3 | Providing and fixing UPVC window | sqm | 165.22 | 1850 | 305657
4 | Brick masonry in CM 1:6 | cum | 166.08 | 3200 | 531456
5 | Providing and laying vitrified tiles 600x600 | sqm | 103.46 | 920 | 95183.2

## Bill Quantity
Agreement No. | 59/2025-25
Name of Work | Construction of Toilet Block at Government College
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing MS door frame | each | 25.67 | 29.1 | 2800
2 | Providing and laying RCC M20 | cum | 53.19 | 54.43 | 6800
3 | Providing and fixing UPVC window | sqm | 89.96 | 127.66 | 1850
4 | Brick masonry in CM 1:6 | cum | 20.4 | 35.8 | 3200
5 | Providing and laying vitrified tiles 600x600 | sqm | 9.94 | 30.55 | 920

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Construction of Toilet Block at Government College
Name of Contractor or supplier : | M/s. Mewar Infra Pvt. Ltd., Chittorgarh
Reference to work order or Agreement : | 59/2025-25
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-05 | 11.2.1 | Providing and fixing ball valve 25mm | 3 | Each | 420 | 1260 | Approved
E-02 | 10.2.3 | Providing and fixing 6A 3-pin socket | 4 | Each | 320 | 1280 | Approved
E-04 | 11.1.2 | Providing and fixing CPVC pipe 25mm | 15 | Rmt | 185 | 2775 | Approved
E-03 | 10.3.1 | Providing and fixing MCB 32A | 2 | Each | 480 | 960 | Approved
| Total |  |  |  |  | 6275