## Title
FOR CONTRACTORS & SUPPLIERS ONLY FOR PAYMENT FOR WORK OR SUPPLIES ACTUALLY MEASURED
Bill Number | BILL-023/2025-26
Agreement No. | 61/2024-25
Name of Work | Construction of Drainage System in Ward No. 5
Name of Contractor or supplier | M/s. Krishna Enterprises, Kota
Work Order Amount Rs. | 2547448
Date of written order to commence work | 18-04-2025
St. Date of Completion | 07-04-2026
Date of actual completion of work
Tender Premium % | 13.05
Premium Type | Below

## Work Order
Agreement No. | 61/2024-25
Name of Work | Construction of Drainage System in Ward No. 5
Name of Contractor or supplier | M/s. Krishna Enterprises, Kota
Work Order Amount Rs. | 2547448
Item | Description | Unit | Qty as per WO | Rate | Amount Rs. | Remarks
1 | Providing and fixing flush door shutter | sqm | 101.39 | 1450 | 147015.5
2 | Plastering 12mm thick CM 1:6 | sqm | 50.7 | 185 | 9379.5
3 | Providing and fixing MS door frame | each | 142.71 | 2800 | 399588
4 | Providing and laying PCC 1:4:8 | cum | 160.83 | 4200 | 675486
5 | Providing and fixing UPVC window | sqm | 75.54 | 1850 | 139749
6 | Brick masonry in CM 1:6 | cum | 65.09 | 3200 | 208288
7 | Providing and laying RCC M20 | cum | 23.42 | 6800 | 159256
8 | Providing and laying vitrified tiles 600x600 | sqm | 123.66 | 920 | 113767.2

## Bill Quantity
Agreement No. | 61/2024-25
Name of Work | Construction of Drainage System in Ward No. 5
Item | Description | Unit | Qty Since Last Bill | Qty Upto Date | Rate | Remarks
1 | Providing and fixing flush door shutter | sqm | 72.43 | 140.99 | 1450
2 | Plastering 12mm thick CM 1:6 | sqm | 21.48 | 26.48 | 185
3 | Providing and fixing MS door frame | each | 134.09 | 169.73 | 2800
4 | Providing and laying PCC 1:4:8 | cum | 98.12 | 120.48 | 4200
5 | Providing and fixing UPVC window | sqm | 100.23 | 114.52 | 1850
6 | Brick masonry in CM 1:6 | cum | 33.2 | 38.41 | 3200
7 | Providing and laying RCC M20 | cum | 41.84 | 90.34 | 6800
8 | Providing and laying vitrified tiles 600x600 | sqm | 176.3 | 185.97 | 920

## Extra Items
EXTRA ITEM SLIP
Name of Work :- | Construction of Drainage System in Ward No. 5
Name of Contractor or supplier : | M/s. Krishna Enterprises, Kota
Reference to work order or Agreement : | 61/2024-25
S.No. | Ref. BSR No. | Particulars | Qty. | unit | Rate | Amount | Remarks
E-04 | 11.1.2 | Providing and fixing CPVC pipe 25mm | 15 | Rmt | 185 | 2775 | Approved
E-02 | 10.2.3 | Providing and fixing 6A 3-pin socket | 4 | Each | 320 | 1280 | Approved
E-03 | 10.3.1 | Providing and fixing MCB 32A | 2 | Each | 480 | 960 | Approved
E-01 | 10.1.1 | Providing and fixing LED light 18W | 2 | Each | 850 | 1700 | Approved
| Total |  |  |  |  | 6715